## Sheet1
Project Wordly
 | time axis 2018-10-15 to 2018-12-11
Who | Major Milestones:
TOGETHER | Data search
Find Appropriate data sets
Clean data
Format data
TOGETHER - UNTIL FIRST TEST IS ACHIEVED | start text prediction algorithm
work for viable test
TEAM 1 | increase accuracy to desired level
TEAM 2 | start GUI design
connect python script with GUI interface
TOGETHER | Start extra features
integrate features with GUI
TOGETHER | last minute checks
TOGETHER! | FINISH! YAY!
NOTE: |  | 2018-10-16: DECISIONS TO BE MADE OR OTHER CONCERNS:
Team 1 and team 2 can be discussed at a later time. |  | 2018-10-16: who takes on which part
If you think the project could be broken down in a better way |  | 2018-10-16: meeting times/schedules
feel free to make some edits and send it out. |  | 2018-10-16: how to work on shared code
this is just a crude outline :) |  | 2018-10-16: version control